## Certificate
Interim payment certificate
Calculated from the Contract, BOQ and Variations sheets.
| Project | Example: Villa G+1, Plot 123
| Contractor | Example Contracting LLC
| Certificate number | 3
Valuation period ending
| Item | Amount (AED)
1 | Work done to date (BOQ) | 204950
2 | Approved variations to date | 21000
3 | Materials on site | 25000
4 | Gross value to date (1 + 2 + 3) | 250950
5 | Less retention (rate × gross, up to the limit) | -25095
6 | Less advance payment recovery (up to the advance) | -25095
7 | Net value to date (4 + 5 + 6) | 200760
8 | Less previously certified | -180000
9 | Amount due this certificate, excl. VAT (7 + 8) | 20760
10 | VAT | 1038
11 | Total payable this certificate (9 + 10) | 21798
Prepared by (contractor)
Certified by (Engineer)
Rates and limits follow your contract. This template is a simple example and not advice.
Quanto Management builds this certificate from the BOQ progress and the Engineer certifies it line by line: quantohq.com

## Contract
Interim payment certificate: contract data
Free template from Quanto (quantohq.com). Fill in the yellow cells; example figures are marked.
Project | Example: Villa G+1, Plot 123
Contractor | Example Contracting LLC
Certificate number | 3
Valuation period ending |  | Enter the date
Contract sum (AED) | 1500000 | Example
Retention rate | 10% | From your contract (example 10%)
Retention limit (share of contract sum) | 5% | From your contract (example 5%)
Advance payment received (AED) | 150000 | Example
Advance recovery rate (share of each valuation) | 10% | From your contract (example 10%)
Materials on site (AED) | 25000 | Where the contract allows payment for them
Previously certified, net (AED) | 180000 | Net amount to date on the last certificate
VAT rate | 5% | UAE standard rate
Yellow cells: your entries. Every other figure is calculated.

## BOQ
Bill of quantities: progress to date
One row per BOQ line. Add rows above the total; the formulas copy down.
Item | Description | Unit | Quantity | Rate (AED) | Amount (AED) | % complete | Value to date (AED)
1.1 | Excavation (example) | m³ | 850 | 25 | 21250 | 100% | 21250
2.1 | Blinding concrete (example) | m³ | 60 | 320 | 19200 | 100% | 19200
2.2 | Reinforced concrete footings (example) | m³ | 140 | 1150 | 161000 | 80% | 128800
3.1 | Blockwork 200 mm (example) | m² | 1200 | 85 | 102000 | 35% | 35700
4.1 | Plaster (example) | m² | 2600 | 32 | 83200 | 0% | 0
| Total |  |  |  | 386650 |  | 204950

## Variations
Approved variations: progress to date
Only approved variations are paid on the certificate.
VO no. | Description | Approved value (AED) | % complete | Value to date (AED)
VO-01 | Additional boundary wall (example) | 42000 | 50% | 21000
VO-02 | Change of floor tiles (example) | 18500 | 0% | 0
| Total | 60500 |  | 21000