## Variations
Variation orders (change orders)
One row per variation. Status: Pending, Submitted, Approved, Rejected.
VO no. | Instruction ref. | Date | Description | Submitted (AED) | Approved (AED) | Days asked | Days approved | Status
VO-01 | SI-004 | 2026-06-14 | Additional boundary wall (example) | 46500 | 42000 | 10 | 7 | Approved
VO-02 | SI-007 | 2026-08-02 | Change of floor tiles (example) | 18500 |  | 0 |  | Submitted
|  |  | Total | 65000 | 42000 | 10 | 7

## Claims
Claims and extension of time
Deadlines are counted from the date you became aware, using the periods on the Settings sheet.
Claim no. | Event | Date aware | Notice due | Detailed claim due | Notice sent | Days left to notice | Status
CL-01 | Late access to site (example) | 2026-09-20 | 2026-10-18 | 2026-12-13 | 2026-10-05 |  | Notice sent
CL-02 | Suspension by the Engineer (example) | 2026-10-12 | 2026-11-09 | 2027-01-04 |  | 18 | Open
Days left counts from today; a negative number means the notice period has passed. Your contract decides the periods.
Formulas:
Notice due = IF([Date aware]="","",[Date aware]+Settings!B5)
Detailed claim due = IF([Date aware]="","",[Date aware]+Settings!B6)
Days left to notice = IF(OR([Date aware]="",[Notice sent]<>""),"",[Notice due]-TODAY())

## Summary
Summary
Calculated from the other sheets.
Original contract sum | 1500000
Approved variations | 42000
Revised contract sum | 1542000
Variations as a share of the contract sum | 2.8%
Extension of time approved through variations (days) | 7
Quanto Management keeps this register for you, linked to instructions, site events and letters: quantohq.com

## Settings
Variation and claims register: settings
Free template from Quanto (quantohq.com). Yellow cells are yours to fill in.
Original contract sum (AED) | 1500000 | Example
Notice of claim period (days) | 28 | FIDIC 2017 Sub-Clause 20.2.1; change to your contract
Detailed claim period (days) | 84 | FIDIC 2017 Sub-Clause 20.2.4; change to your contract